## Gantt_Weekly_Auto
ID | Task | Phase | Owner | Start | End | % Complete | 2025-11-03 | 2025-11-10 | 2025-11-17 | 2025-11-24 | 2025-12-01 | 2025-12-08 | 2025-12-15 | 2025-12-22 | 2025-12-29 | 2026-01-05 | 2026-01-12 | 2026-01-19 | 2026-01-26 | 2026-02-02 | 2026-02-09 | 2026-02-16 | 2026-02-23
T1 | Requirements finalization | Planning | Team | 2025-11-03 | 2025-11-10 | 100
T2 | System design & API spec | Planning | Team | 2025-11-03 | 2025-11-10 | 90
T3 | Prompt design outline | Planning | Team | 2025-11-03 | 2025-11-10 | 50
T4 | K8s + CI/CD readiness check | Planning | Team | 2025-11-03 | 2025-11-10 | 30
T5 | Data tools: trades/market data/quotes | Build |  | 2025-11-10 | 2025-12-01 | 20
T6 | REST agent service scaffold | Build |  | 2025-11-10 | 2025-12-01 | 10
T7 | Agent model & tool wiring | Build |  | 2025-11-10 | 2025-12-01 | 5
T8 | Auth JWT bearer | Build |  | 2025-11-10 | 2025-12-01 | 0
T9 | Logging + tracing base | Build |  | 2025-11-10 | 2025-12-01 | 0
T10 | Prompt refinement | Agent Logic |  | 2025-12-01 | 2025-12-15 | 0
T11 | Win-rate logic | Agent Logic |  | 2025-12-01 | 2025-12-15 | 0
T12 | Payoff suggestion logic | Agent Logic |  | 2025-12-01 | 2025-12-15 | 0
T13 | Quote UI updates | UI & Deploy |  | 2025-12-15 | 2025-12-22 | 0
T14 | K8s deployment scripting | UI & Deploy |  | 2025-12-15 | 2025-12-22 | 0
T15 | CI/CD full pipeline | UI & Deploy |  | 2025-12-15 | 2025-12-22 | 0
T16 | Load/testing & feedback | Integration | All | 2025-12-22 | 2025-12-29 | 0
T17 | UAT | UAT | Users | 2026-01-01 | 2026-01-31 | 0
T18 | Prod rollout | Production |  | 2026-02-01 | 2026-02-05 | 0

## Milestones
Milestone ID | Milestone | Date | Owner | Status | Notes
M1 | Design Complete | 2025-11-10 | Dev Lead | Pending
M2 | Backend Ready | 2025-12-01 | Dev A | Pending
M3 | Agent Ready | 2025-12-15 | Dev B | Pending
M4 | UI + Deployment Ready | 2025-12-22 | Dev C | Pending
M5 | UAT Start | 2026-01-01 | Users | Pending
M6 | Go-Live | 2026-02-05 | Ops | Pending

## Resource_Load
Week Start | 2025-11-03 | 2025-11-10 | 2025-11-17 | 2025-11-24 | 2025-12-01 | 2025-12-08 | 2025-12-15 | 2025-12-22 | 2025-12-29 | 2026-01-05 | 2026-01-12 | 2026-01-19 | 2026-01-26 | 2026-02-02 | 2026-02-09 | 2026-02-16 | 2026-02-23
Dev A | 40 | 100 | 60 | 60 | 60 | 0 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Dev B | 40 | 60 | 20 | 20 | 80 | 60 | 60 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Dev C | 40 | 60 | 20 | 20 | 20 | 0 | 60 | 80 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total/Week | 120 | 220 | 100 | 100 | 160 | 60 | 120 | 120 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## JIRA_Import_Template
Summary | Issue Type | Description | Priority | Assignee | Reporter | Start Date | Due Date | Epic Link
Requirements finalization | Task | Planning - Requirements finalization | High | Dev A | PM | 2025-11-03 | 2025-11-10 | AI-Agent-EPIC
System design & API spec | Task | Planning - System design & API spec | High | Dev A/B/C | PM | 2025-11-03 | 2025-11-10 | AI-Agent-EPIC
Prompt design outline | Task | Planning - Prompt design outline | High | Dev B | PM | 2025-11-03 | 2025-11-10 | AI-Agent-EPIC
K8s + CI/CD readiness check | Task | Planning - K8s + CI/CD readiness check | High | Dev C | PM | 2025-11-03 | 2025-11-10 | AI-Agent-EPIC
Data tools: trades/market | Task | Build - Data tools: trades/market | High | Dev A | PM | 2025-11-10 | 2025-12-01 | AI-Agent-EPIC
REST agent service scaffold | Task | Build - REST agent service scaffold | High | Dev A | PM | 2025-11-10 | 2025-12-01 | AI-Agent-EPIC
Agent model & tool wiring | Task | Build - Agent model & tool wiring | High | Dev B | PM | 2025-11-10 | 2025-12-01 | AI-Agent-EPIC
Auth JWT bearer | Task | Build - Auth JWT bearer | High | Dev A | PM | 2025-11-10 | 2025-12-01 | AI-Agent-EPIC
Logging + tracing base | Task | Build - Logging + tracing base | High | Dev C | PM | 2025-11-10 | 2025-12-01 | AI-Agent-EPIC
Prompt refinement | Task | Agent Logic - Prompt refinement | High | Dev B | PM | 2025-12-01 | 2025-12-15 | AI-Agent-EPIC
Win-rate logic | Task | Agent Logic - Win-rate logic | High | Dev B | PM | 2025-12-01 | 2025-12-15 | AI-Agent-EPIC
Payoff suggestion logic | Task | Agent Logic - Payoff suggestion logic | High | Dev B | PM | 2025-12-01 | 2025-12-15 | AI-Agent-EPIC
Quote UI updates | Task | UI & Deploy - Quote UI updates | High | Dev C | PM | 2025-12-15 | 2025-12-22 | AI-Agent-EPIC
K8s deployment scripting | Task | UI & Deploy - K8s deployment scripting | High | Dev C | PM | 2025-12-15 | 2025-12-22 | AI-Agent-EPIC
CI/CD full pipeline | Task | UI & Deploy - CI/CD full pipeline | High | Dev C | PM | 2025-12-15 | 2025-12-22 | AI-Agent-EPIC
Load/testing & feedback | Task | Integration - Load/testing & feedback | High | All | PM | 2025-12-22 | 2025-12-29 | AI-Agent-EPIC
UAT | Task | UAT - UAT | High | Users | PM | 2026-01-01 | 2026-01-31 | AI-Agent-EPIC
Prod rollout | Task | Production - Prod rollout | High | DevOps | PM | 2026-02-01 | 2026-02-05 | AI-Agent-EPIC

## Portfolio_View
Workstream | Task | Start | End | Owner | Status
Core Platform | Requirements finalization | 2025-11-03 | 2025-11-10 | Dev A | On Track
Core Platform | System design & API spec | 2025-11-03 | 2025-11-10 | Dev A/B/C | On Track
Core Platform | Prompt design outline | 2025-11-03 | 2025-11-10 | Dev B | On Track
Core Platform | K8s + CI/CD readiness check | 2025-11-03 | 2025-11-10 | Dev C | On Track
Core Platform | Data tools: trades/market | 2025-11-10 | 2025-12-01 | Dev A | On Track
Core Platform | REST agent service scaffold | 2025-11-10 | 2025-12-01 | Dev A | On Track
Core Platform | Agent model & tool wiring | 2025-11-10 | 2025-12-01 | Dev B | On Track
Core Platform | Auth JWT bearer | 2025-11-10 | 2025-12-01 | Dev A | On Track
Core Platform | Logging + tracing base | 2025-11-10 | 2025-12-01 | Dev C | On Track
Agent/UX | Prompt refinement | 2025-12-01 | 2025-12-15 | Dev B | On Track
Agent/UX | Win-rate logic | 2025-12-01 | 2025-12-15 | Dev B | On Track
Agent/UX | Payoff suggestion logic | 2025-12-01 | 2025-12-15 | Dev B | On Track
Agent/UX | Quote UI updates | 2025-12-15 | 2025-12-22 | Dev C | On Track
Agent/UX | K8s deployment scripting | 2025-12-15 | 2025-12-22 | Dev C | On Track
Agent/UX | CI/CD full pipeline | 2025-12-15 | 2025-12-22 | Dev C | On Track
Core Platform | Load/testing & feedback | 2025-12-22 | 2025-12-29 | All | On Track
Agent/UX | UAT | 2026-01-01 | 2026-01-31 | Users | On Track
Agent/UX | Prod rollout | 2026-02-01 | 2026-02-05 | DevOps | On Track